Security Improvement Plan

GreenFields Food Processing Ltd.

Branko Džakula | Student ID: 35250238  |  March 2026  |  Confidential

# 1. Security Maturity Assessment

GreenFields Food Processing currently operates at an overall security maturity of Level 0–1 (Non-existent to Ad-hoc) across all domains. The company has 120 employees, 3 IT staff, 2 production plants and 1 headquarters, with 155 endpoints (90 laptops, 30 industrial PCs, 20 warehouse scanners, 15 smartphones) and 20 virtual machines on 4 hosts. There are no security policies, no risk assessment, no incident response plan, no security training, and no security monitoring. Three recent incidents (supplier ransomware, successful phishing credential theft, lost laptop) demonstrate that the threat environment is active while defences are essentially absent.

The most dangerous finding is the absence of network segmentation: the 30 industrial production PCs and production systems share the same network as corporate endpoints. A single compromised laptop could directly reach production infrastructure. Combined with backups stored on the same network, a ransomware event could simultaneously encrypt production, corporate, and backup systems.

| Security Domain | Current Level | Target (18 mo.) | Evidence / Gaps |
| --- | --- | --- | --- |
| Risk Management | Level 0 | Level 2 | No risk assessment ever performed; no risk register exists |
| Security Policies | Level 0 | Level 2 | No security policies of any kind; no acceptable use, no access control policy |
| Access Control | Level 1 (Ad-hoc) | Level 3 | Shared admin passwords in use; no RBAC; no MFA on any system |
| Network Security | Level 0 | Level 2 | Production and corporate on same LAN; no segmentation; no IDS/IPS |
| Endpoint Protection | Level 1 (Ad-hoc) | Level 2 | Basic antivirus only; no EDR; inconsistent patching on 155 endpoints |
| Backup & Recovery | Level 1 (Ad-hoc) | Level 3 | Backups exist but stored on same network; never tested; no offsite copy |
| Incident Response | Level 0 | Level 2 | No IR plan; no playbooks; no assigned roles; ad-hoc response to incidents |
| Security Awareness | Level 0 | Level 2 | Zero training delivered; phishing credential loss already occurred |
| Monitoring & Logging | Level 0 | Level 2 | No SIEM; no log collection; no alerting; breaches would go undetected |
| Vendor / Supply Chain | Level 0 | Level 1 | No vendor security assessments; supplier ransomware already impacted operations |

# 2. Top 10 Cybersecurity Risks

Risks are scored on a 5×5 matrix (Likelihood × Impact). L: 1=Rare, 2=Unlikely, 3=Possible, 4=Likely, 5=Almost Certain. I: 1=Negligible, 2=Minor, 3=Moderate, 4=Major, 5=Catastrophic. Ratings: Critical (20–25), High (12–19), Medium (6–11), Low (1–5). Each risk is linked to evidence from the case study.

| # | Risk Scenario | L | I | Score | Rating | Basis / Evidence |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Ransomware encrypts ERP and production systems, halting food production and shipments | 4 | 5 | 20 | Critical | Supplier already hit; production network on same LAN as corporate; backups on same network would also be encrypted |
| 2 | Phishing attack steals employee credentials, giving attacker access to M365 and internal systems | 5 | 4 | 20 | Critical | Already happened once (credential theft on fake site); no MFA; no training; 120 employees as attack surface |
| 3 | Production network compromise via lateral movement from corporate LAN | 4 | 5 | 20 | Critical | No segmentation; 30 industrial PCs and production systems directly reachable from any corporate endpoint |
| 4 | Backup failure during disaster: backups are on same network, encrypted or corrupted alongside production data | 4 | 5 | 20 | Critical | Backups stored on same network segment; ransomware routinely targets network shares; no offsite or offline copy; never tested |
| 5 | Lost/stolen endpoint exposes confidential business data or credentials | 4 | 3 | 12 | High | Already happened: laptop with internal documents lost during travel; no full-disk encryption; no remote wipe capability |
| 6 | Shared admin password compromise leads to complete infrastructure takeover | 3 | 5 | 15 | High | Shared admin passwords in use across systems; if compromised (phishing, brute-force, ex-employee), attacker has full control |
| 7 | Unpatched vulnerability exploited on endpoints or servers | 4 | 4 | 16 | High | Patch management is inconsistent; 4 hosts + 20 VMs + 155 endpoints with unknown patch status; known exploitation path |
| 8 | Supply chain attack via compromised supplier/vendor system | 3 | 4 | 12 | High | Supplier ransomware already occurred; no vendor security requirements; ERP integrates with external logistics partners |
| 9 | Insider threat: employee with shared admin access exfiltrates or destroys data | 2 | 5 | 10 | Medium | Shared admin passwords mean no accountability; no DLP; no audit logging; disgruntled employee could cause major damage |
| 10 | Regulatory non-compliance (GDPR) due to lack of security controls and documentation | 3 | 4 | 12 | High | Employee/customer data processed with no policies, no DPIA, no breach notification process; fines up to 4% of €25M |

# 3. Priority Security Improvements

Each improvement is selected for maximum risk reduction relative to cost and implementation effort, given a 3-person IT team and a requirement to minimize production downtime. Improvements are ordered by recommended implementation sequence.

| # | Improvement | Type | What and Why |
| --- | --- | --- | --- |
| 1 | Network Segmentation | Technical | Separate corporate, production, and guest into isolated VLANs with firewall rules. Prevents any corporate-side compromise from reaching 30 industrial PCs. Without this, a single breach reaches everything. |
| 2 | MFA on All Critical Systems | Technical | Enforce MFA on M365, ERP, VPN, admin accounts. Phishing already stole credentials once; MFA would have prevented it. Blocks >99% of credential attacks. Best risk-reduction per euro. |
| 3 | Offsite Backup + Monthly Testing | Technical | 3-2-1 rule: local + offsite cloud copy with separate credentials. Monthly restore tests. Current backups on same network would be encrypted alongside production by ransomware. |
| 4 | Security Awareness Training | Organizational | Quarterly phishing sims + annual training for 120 staff. Phishing already succeeded once. Reduces click rates from ~30% to <10% within a year. |
| 5 | Endpoint Detection & Response | Technical | Managed EDR on 120 endpoints (laptops + industrial PCs). Behavioral detection catches ransomware when signatures fail. Gives 3-person IT team managed SOC capability. |
| 6 | Eliminate Shared Admin Accounts | Organizational | Individual named admin accounts with logging. Disable shared credentials in 30 days. Shared passwords = zero attribution; one phishing success gives full admin access. |
| 7 | Patch Management Programme | Technical | Monthly patch cycle for 155 endpoints + 20 VMs. Critical patches <7 days. Production patches in maintenance windows. Closes the most common exploitation path. |
| 8 | Incident Response Plan | Organizational | Documented IR plan with roles + playbooks for ransomware, phishing, breach. Semi-annual tabletop exercises. Without a plan, response will be chaotic and expensive. |
| 9 | Full-Disk Encryption + Remote Wipe | Technical | BitLocker on 90 laptops + 15 phones. Remote wipe via Intune. Laptop already lost with documents; encryption prevents data breaches from lost devices. |
| 10 | Basic Security Policies | Organizational | Five core policies: Acceptable Use, Access Control, Backup, IR, Vendor Security. No current governance baseline; policies are the foundation for enforcement and compliance. |

# 4. Implementation Roadmap (12–18 Months)

The roadmap follows a phased approach: Phase 1 delivers quick wins with immediate risk reduction and minimal disruption. Phase 2 tackles infrastructure changes requiring planning and maintenance windows. Phase 3 establishes governance processes for long-term sustainability. This sequencing ensures the 3-person IT team is not overwhelmed and production downtime is minimized.

| Phase | Timeline | Initiatives | Key Milestones |
| --- | --- | --- | --- |
| Phase 1: Immediate | Months 1–4 | MFA rollout; security awareness training launch; eliminate shared admin accounts; offsite backup setup + first test; core security policies drafted | MFA active for 100% of users (month 2); first phishing sim completed (month 3); first successful backup restore (month 4); policies approved by management (month 4) |
| Phase 2: Medium-term | Months 5–10 | Network segmentation (corporate/production/guest); EDR deployment on 120 endpoints; patch management tool + monthly cycle; full-disk encryption on all laptops + phones | Segmentation live (month 8); EDR coverage 100% (month 7); patch compliance >90% (month 9); BitLocker on all mobile devices (month 6) |
| Phase 3: Strategic | Months 11–18 | Incident response plan + first tabletop exercise; vendor security questionnaire for top suppliers; security monitoring baseline (M365 audit logs + alerting); annual security review | IR plan approved + first tabletop (month 12); vendor assessments completed for top 5 suppliers (month 14); monitoring dashboard live (month 13); full programme review at month 18 |

# 5. Budget Allocation (€80,000/year)

The budget prioritises high-impact, low-cost items first (MFA at €2,500 is the best risk-reduction per euro). The total Year 1 spend is €62,000, leaving an €18,000 reserve for Year 2 programme expansion (e.g., SIEM, penetration testing, advanced vendor management). Network segmentation is the largest single cost (€18,000) but is justified because it is the single control that most reduces the blast radius of every other risk.

| Item | Phase | Cost | Notes |
| --- | --- | --- | --- |
| MFA Implementation | 1 | €2,500 | M365 Conditional Access (included in license) + hardware tokens for plant staff |
| Security Awareness Platform | 1 | €4,000/yr | Cloud platform with phishing sim + training modules for 120 users |
| Offsite Backup (cloud replication) | 1 | €5,000/yr | Cloud backup target with immutable retention; separate credentials |
| Network Segmentation | 2 | €18,000 | Managed switches, VLAN config, firewall rules; largest single investment but highest impact |
| EDR (Managed) | 2 | €14,000/yr | Managed EDR for ~120 endpoints (laptops + industrial PCs); includes SOC monitoring |
| Patch Management Tooling | 2 | €3,000/yr | WSUS or cloud-based patching; includes OT maintenance window scheduling |
| Full-Disk Encryption (BitLocker + Intune) | 2 | €2,000 | Intune licensing + enrollment effort; BitLocker is included in Windows Pro |
| Incident Response Plan (external consultant) | 3 | €5,000 | External consultant to draft IR plan and facilitate 2 tabletop exercises |
| Vendor Security Assessments | 3 | €1,500 | Questionnaire platform + internal effort for top 5 supplier reviews |
| Policy Development (internal effort) | 1 | €0 | Written by IT team with management input; no external cost, only time |
| Contingency Reserve (10%) | — | €7,000 | Buffer for unplanned costs, scope changes, or emergency response needs |
| TOTAL | — | €62,000 | Well within €80,000 budget; €18,000 reserve for Year 2 programme expansion |

# 6. Security KPIs for Management

These five KPIs were selected because they are: directly tied to the top risks, objectively measurable (not subjective maturity scores), actionable (each KPI failure points to a specific improvement that needs attention), and reportable to management quarterly in a simple dashboard format.

| # | KPI | Baseline (Today) | Target (12 months) | How to Measure |
| --- | --- | --- | --- | --- |
| 1 | Phishing Click Rate | Unknown (est. >30% based on industry avg.) | <10% | Quarterly phishing simulations via awareness platform; track click rate trend over time |
| 2 | MFA Coverage | 0% (no MFA on any system) | 100% for M365, ERP, VPN, admin accounts | M365 Conditional Access reports; ERP/VPN admin audit; monthly compliance check |
| 3 | Patch Compliance Rate | Unknown (ad-hoc patching) | >90% within 30 days; critical <7 days | Patch management tool reports; monthly scan of all 155 endpoints and 20 VMs |
| 4 | Backup Restore Success | 0% (never tested) | 100% monthly success rate | Documented monthly restore test to isolated environment; pass/fail log reviewed by IT Manager |
| 5 | Mean Time to Detect + Contain Incidents | Undefined (no process) | Detection <24h; containment <8h | Incident register timestamps; measured from first alert to confirmed containment; reviewed after each incident |